## SEO Roadmap
SEO Roadmap — Imago Photography ¦ August & September 2026
Category | Activity | Owner | Aug W1 1–7 | Aug W2 8–14 | Aug W3 15–21 | Aug W4 22–31 ★ Schools search | Sep W1 1–7 | Sep W2 8–14 | Sep W3 15–21 | Sep W4 22–30 | Priority
CONTENT — Blogs
Content | July Blog 2 — Publish once Will approves | Senthil | ● | [7 empty] | Critical
| Aug Blog 1 — Write draft | Ashish / Simran | ● | ● | [6 empty] | Critical
| Aug Blog 1 — Will approves & Senthil publishes | Will / Senthil |  | ● | ● | [5 empty] | Critical
| Aug Blog 2 — Write draft | Ashish / Simran |  |  | ● | [5 empty] | High
| Aug Blog 2 — Will approves & Senthil publishes | Will / Senthil |  |  | ● | ● |  |  |  |  | High
| Sep Blog 1 — Write draft | Ashish / Simran |  |  |  | ● | ● |  |  |  | High
| Sep Blog 1 — Will approves & Senthil publishes | Will / Senthil |  |  |  |  | ● | ● |  |  | High
| Sep Blog 2 — Write draft | Ashish / Simran | [5 empty] | ● | ● |  | Medium
| Sep Blog 2 — Will approves & Senthil publishes | Will / Senthil | [6 empty] | ● | ● | Medium
TECHNICAL SEO — Website & Tracking
Technical | Website fixes live — CAPTCHA, forms, Thank You pages, GTM | Senthil | ● | [7 empty] | Critical
| GA4 conversion tracking update (after fixes live) | Ashish | ● | [7 empty] | Critical
| FAQ schema — implement on website | Senthil | ● | ● | [6 empty] | High
| SEO audit fixes — Critical items | Senthil |  | ● | ● | [5 empty] | Critical
| SEO audit fixes — Important items | Senthil |  |  |  | ● | ● |  |  |  | High
| SEO audit fixes — Good to have | Senthil | [5 empty] | ● | ● |  | Low
OFF-PAGE — Quora, Reddit, Medium
Off-Page | Quora — 1 answer per week (write, share with Will, post) | Ashish | ● | ● | ● | ● | ● | ● | ● | ● | High
| Reddit — 3 answers live (once Will approves topics) | Ashish | ● | [7 empty] | High
| Medium — Article 1 (write, Will approves, publish) | Ashish | ● | ● | [6 empty] | High
| Medium — Article 2 (write, Will approves, publish) | Ashish |  |  | ● | ● |  |  |  |  | Medium
| Medium — Article 3 (write, Will approves, publish) | Ashish |  |  |  |  | ● | ● |  |  | Medium
| Republish existing blogs on Medium with backlinks | Ashish | ● | ● | [6 empty] | Medium
GMB & LOCAL — Google Business Profile
GMB | GMB access — Will to upgrade Ashish to Owner | Will | ● | [7 empty] | Critical
| GMB social profiles — add Instagram, Facebook, YouTube | Ashish | ● | [7 empty] | High
| GMB founding date — confirm and update once Will confirms | Ashish | ● | [7 empty] | Medium
| Review acquisition — continue email + QR code outreach | Laura | ● | ● | ● | ● | ● | ● | ● | ● | Medium
REPORTING & ANALYTICS
Reporting | Keyword ranking plan — share with Harshit | Ashish | ● | [7 empty] | High
| LLM visibility check — ChatGPT, Perplexity, Google AI | Ashish | ● |  |  |  | ● |  |  |  | Medium
| August SEO dashboard — Harshit reviews, then to Will | Ashish / Harshit |  |  |  | ● |  |  |  |  | Critical
| September SEO dashboard — Harshit reviews, then to Will | Ashish / Harshit | [7 empty] | ● | Critical
| YoY traffic comparison in dashboard (Will's requirement) | Ashish |  |  |  | ● |  |  |  | ● | High
● = Active that week ★ Aug W4 = Last week of August — schools begin searching for photographers