## SEO Activity Plan
SEO Activity Plan — Imago Photography ¦ August & September 2026
Focus: Maintain and grow traffic and rankings ¦ Senthil (developer) has limited time — activities prioritised accordingly
Category | Activity | What We Do | Why It Matters / Goal | Owner | Priority | August | September
Technical SEO | Website Fixes (Forms, CAPTCHA, Thank You pages, GTM) | CAPTCHA on enquiry and booking forms. Thank You page after each submission. GTM tag firing confirmed. | Without this, GA4 shows bot-inflated form submissions. We cannot measure real leads accurately. | Senthil | Critical | Go live ASAP — top of Senthil's list | Monitor and confirm data is clean
| GA4 Conversion Tracking Update | Update GA4 goals to track Thank You page URLs once Senthil confirms they are live. | Ensures every real enquiry and booking is counted. Gives Will accurate lead data each month. | Ashish | Critical | Immediately after Senthil confirms fixes live | Ongoing — confirm clean data in dashboard
| FAQ Schema Implementation | Add FAQPage structured data code to the website so FAQs appear in Google search results. | FAQ schema can earn extra space in search results and improve click-through rate with no ongoing effort. | Senthil | High | Implement once Will approves FAQ copy | Monitor for rich result appearance in Search Console
| SEO Audit Fixes — Critical Items | Implement the top-priority fixes from the blog page audit, as ranked in the shared document. | These are the fixes with the highest direct impact on rankings. Delay costs ranking positions. | Senthil | Critical | Begin as soon as website fixes are live | Complete remaining critical fixes
| SEO Audit Fixes — High Priority Items | Second tier of audit fixes — meaningful impact but not immediate. | Keeps the site technically healthy ahead of the September peak season. | Senthil | High | Start if time allows in August | Complete by end of September
On-Page SEO | Keyword Targeting — Blog and Page Content | Ensure all blogs and pages target primary and secondary keywords. Keywords highlighted in documents so editors do not remove them. | Organic rankings depend on pages being clearly relevant to the search terms schools use. Keywords in copy = rankings. | Ashish | High | Add primary and secondary keywords to all August blog drafts | Repeat for September blogs
| How to Choose Blog — Content Fix | Will to send corrected blog content. Ashish to review and pass to Senthil to update on website. | This blog targets high-value search terms. Incorrect content hurts credibility and ranking. | Will → Ashish → Senthil | High | Chase Will for corrected content — implement once received | Confirm live and indexed
Content | August Blogs — 2 per month | Write two blogs targeting school photography keywords. Share with Harshit, then Will for approval. Senthil publishes. | Fresh, targeted content builds topical authority and earns rankings over time. Peak season content must be live before schools search. | Ashish / Simran → Will → Senthil | Critical | Topics to be approved by Will. Both blogs written, approved, and published by end of August. | Both blogs indexed and appearing in Search Console
| September Blogs — 2 per month | Two September blogs focused on individual school photography (peak season topic). Same approval process. | September is the start of individual school photo season — schools are actively searching. Content must match what they are looking for. | Ashish / Simran → Will → Senthil | High | Write September Blog 1 by end of August so it can go live week 1 of September | Both blogs live. September Blog 2 published by mid-September.
| FAQs — Final Approval and Publish | Will to review highlighted FAQs and approve. Senthil to publish on the website with schema. | FAQs target question-based searches (how, what, which) and can appear in Google's People Also Ask section. | Will → Senthil | High | Chase Will approval — aim to publish in August | Monitor for PAA and FAQ rich result appearances
Off-Page / Backlinks | Quora — Weekly Answers | Write one Quora answer per week, share with Will for approval, then post. Links back to Imago website. | Quora answers appear in Google search results and AI answers. Each answer is a signal to LLMs that Imago is a credible source. | Ashish → Will | High | 4 answers — one per week, all approved before posting | 4 more answers. Build a visible Quora presence by end of September.
| Reddit — 3 Approved Answers | Answer 3 identified Reddit threads. Will has approved the questions. Drafts to be written and shared before posting. | Reddit content is heavily cited by ChatGPT and Perplexity. Being present there improves Imago's AI visibility. | Ashish → Will | High | Write and post all 3 answers once Will approves drafts | Monitor for citations in AI search tools
| Medium Articles — Backlinks to Imago | Write 2 articles per month on the Imago Medium account. Each links back to the main website. Will to approve before publishing. | Medium articles rank on Google and create backlinks. They also help Imago appear in AI-generated answers. | Ashish → Will | Medium | Article 1 and 2 written, approved, and live | Article 3 and 4 live. 4 Medium articles total by end of September.
| Republish Existing Blogs on Medium | Take existing Imago blogs and republish them on Medium with backlinks to the main website. | Zero extra writing effort — uses content already approved. Creates additional backlinks and extends each blog's reach. | Ashish | Medium | Republish 2–3 existing blogs on Medium in August | Continue republishing remaining blogs
Reporting | Monthly SEO Dashboard — August | Prepare dashboard covering traffic, rankings, clicks, backlinks, and AI visibility. Harshit reviews first, then share with Will. | Will needs monthly data to see if SEO is working. YoY comparison is required — he has asked for this specifically. | Ashish → Harshit → Will | Critical | Share with Harshit by 18 August. To Will by 20 August. | —
| Monthly SEO Dashboard — September | Same as August. Include YoY comparison and note any ranking changes from peak season traffic. | September data will show whether pre-season content work translated into real traffic and ranking gains. | Ashish → Harshit → Will | Critical | — | Share with Harshit by 18 Sep. To Will by 20 Sep.
| Keyword Ranking Plan | Share the keyword ranking plan with Harshit — which keywords we are targeting, current positions, and target positions. | Gives Harshit visibility of what we are trying to rank for so he can align content and off-page activity. | Ashish → Harshit | High | Share with Harshit in first week of August | Update with any ranking movements
| LLM Visibility Check (ChatGPT, Perplexity, Google AI) | Search for Imago in ChatGPT, Perplexity, and Google AI Overviews. Record whether Imago is mentioned. | AI search is growing. Knowing whether Imago appears in AI answers tells us if the GEO/AEO strategy is working. | Ashish | Medium | Baseline check — record August results | Second check — compare with August. Report any improvement.