## SEO Activity Plan
Activity | What Damco Handles | What We Need From You | Due Date | Status
Blog — July post 1 "Why Professional School Photography Matters" | Written and ready to publish | Senthil to upload to website | ASAP — discussed 22 Jul | Waiting on Senthil
Blog — July post 2 "Why School Photography Matters / What to Look for in a New Photographer" | Writing in progress | Review draft when shared, then approve | 24 July 2026 | Waiting on Will
Blog — "How to Choose a School Photography Company in the UK" | Published on website — SEO audit done, fixes sent to Senthil | Will to send corrected blog content | ASAP | Waiting on Will
FAQs | Written and ready — schema code prepared for Senthil | Will to complete review and approve | ASAP | Waiting on Will
Website Fixes (Forms, CAPTCHA, Thank You pages) | Specifications sent to Senthil with full detail | Senthil to implement and confirm live date | ASAP | Waiting on Senthil
Quora | Damco writes all answers — nothing for your team to write | Review draft answers before we post — quick read and approve | Ongoing — weekly | In Progress
Reddit | Damco writes all answers — nothing for your team to write | Confirm the 3 questions shared are relevant topics for Imago | 29 July 2026 | Waiting on Will
Medium / Third-Party Articles | Damco writes all articles and manages the account | Review each article draft before we publish — approve or request changes | Ongoing | In Progress
SEO Audit — Blog Pages | Damco audits all published blogs and sends fixes to Senthil | No action needed from Will's side | Ongoing | In Progress
Monthly SEO Dashboard | Damco prepares and shares every month | Review the report — flag any questions | End of each month | In Progress
LLM Visibility (ChatGPT, Perplexity, Google AI) | Damco monitors and builds citations across platforms | No action needed from Will's side | Monthly check — 31 July 2026 | In Progress

## 22 Jul 2026 — Call Agenda
Call Agenda — Imago Photography ¦ 22 July 2026
Topic | Discussion Points | What We Need / Outcome | Owner | Priority | Due Date
Blog SEO — On-Page | • Blog 1 ("Why Professional School Photography Matters") — Will has shared both blogs for review • Blog 2 ("Why School Photography Matters") — review draft received • Confirm Senthil's live date for Blog 1 on website | Confirm live date for Blog 1. Get Will's approval on Blog 2 draft | Ashish | High | 24 July 2026
Reddit Approval | • 3 questions shared — still pending Will's sign-off • r/photography — school photography discussion • r/Nikon — share Imago's images as brand expression • r/UKParenting — UK parents discussing school photo packages • Reminder: Damco writes everything, no time from Will's team needed | Yes or no on each question — approval to post | Will | High | 29 July 2026
SEO Audit Fixes | • Fixes sent to Senthil on 8 July — headings, internal links, meta title/description, alt text, schema • Without these fixes the blog will not rank regardless of content quality • Fixes have been ranked by impact (see SEO Audit Priority sheet) | Agree a deadline for all fixes to go live | Senthil | High | 29 July 2026
Web Page Content — Pending Updates | • Damco shared content suggestions for multiple web pages • School Photography page — changes applied after audit • All remaining pages still pending — content updates not yet applied • Agree which pages to prioritise next | Confirm remaining pages are on Senthil's list. Agree priority order and deadline for next batch | Senthil / Ashish | Medium | 29 July 2026
August Blog Topics | • Recommend back-to-school angle — positions Imago for September search traffic • Suggest 2 topics for Will to approve today so writing can begin • Topics must be approved before writing starts | Will approves 2 blog topics for August | Ashish / Will | Medium | 29 July 2026
GTM Implementation | • GTM setup assigned to Senthil • Thank You page part to be revised as part of this • Confirm Senthil has received requirements and access | Senthil confirms live date for GTM implementation | Senthil | Medium | 29 July 2026
Quora Update | • 2 answers posted this month — "How are large schools photographed?" and "How can parents prepare kids?" • Cadence: 1 per week — Damco shares draft before posting • Will to share Quora drafts for review today | Will confirms approval process is working | Ashish | Low | Ongoing

## SEO Audit — Priority Fixes
SEO Audit — Blog Fixes Ranked by Impact ¦ How to Choose a School Photography Company
Fixes are ranked in order of SEO impact. Start with Critical — these have the highest effect on rankings. Do Important next. Good to have can wait.
Fix Required | Why It Matters | Impact Level | Owner
3 H1 tags on the page (should be 1 only) | Multiple H1s split ranking signals — search engines cannot determine the primary topic of the page | Critical — do first | Senthil
Article title coded as H3 instead of H2 | Heading hierarchy must flow H1 → H2 → H3. Incorrect structure reduces how well search engines read the content | Critical — do first | Senthil
All section headings are H3 — no H2 used | Page jumps from H1 straight to H3 with no H2, breaking content structure for search engines | Critical — do first | Senthil
No Article schema on the page | Schema helps search engines understand the content type and can improve how the page appears in results | Critical — do first | Senthil
Only 1 internal link — 10 more identified | Internal links help search engines discover other pages and pass authority across the site | Important — do next | Senthil
Title tag is 74 characters (max 60) | Titles over 60 characters are cut off in search results, reducing click-through rates | Important — do next | Senthil
Meta description is 122 characters (min 150–160) | Short descriptions reduce click-through rates — search engines may auto-generate a less relevant snippet | Important — do next | Senthil
2 images missing alt text | Alt text helps search engines understand images and is required for accessibility compliance | Good to have — when ready | Senthil
No outbound links to credible sources | Authoritative content is expected to reference credible sources, particularly on trust-sensitive topics like safeguarding | Good to have — when ready | Senthil